## JAN
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba School
Reporting Period | JAN
Total Working Days a month | 21
Total Number of Workers | 37
Total Man-Hours Worked | 6216
Safety Performance :
Number of Safety Inspections | 1
Number of Safety Observation Raised | 6
Number of Safety Observation Closed | 5 | FS2 play area Fence still pending - Layout
External HSE Inspection / Audits | 0
Number of Safety Meetings Held | 1
Near Miss Reported | 3
Emergency Drills and Preparedness | 1
Incident Reporting :
Elevator | 0
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 1
Occupational Illness/Diseases | 0
Medical Treatment Case | 0
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 0
Water Leaks/ Flooding | MEP LOG
Incident Frequency Rates
LTIFR - Lost Time Injury Frequency Rate | 0
TRIR - Total Recordable Incident Rate | 1
Training and Safety Programs
Number of Safety Trainings | 2
Training Topic 1 : | HSE Induction
Training Topic 2 : | Risk Assessment, Method of Work & Standard Operating Procedures
Training Topic 3 : | N/A
Number of Safety TBT | 4
TBT Topic 1 : | Ladder Safety Training
TBT Topic 2 : | Child Protection & Abuse Prevention
TBT Topic 3 : | Personal Protective Equipment (PPE)
TBT Topic 4 : | Work at Height Safety Training
TBT Topic 5 : | N/A
Safety Awards and Recognitions | N/A
Recommendations and Improvements | N/A

## FEB
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba School
Reporting Period | FEB |  | Working Days = 21
Total Working Days a month | 21
Total Number of Workers | 37
Total Man-Hours Worked | 6216
Safety Performance :
Number of Safety Inspections | 1
Number of Safety Observation Raised | 7
Number of Safety Observation Closed | 7
External HSE Inspection / Audits | 1 | ESE HSE Inspection
Number of Safety Meetings Held | 1
Near Miss Reported | 2
Emergency Drills and Preparedness | 0
Incident Reporting :
Elevator | 0
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 0
Occupational Illness/Diseases | 0
Mdical Treatment Case | 0
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 0
Water Leaks/ Flooding | MEP LOG
Incident Frequency Rates
LTIFR - Lost Time Injury Frequency Rate | 0
TRIR - Total Recordable Incident Rate | 2
Training and Safety Programs
Number of Safety Trainings | 2
Training Topic 1 : | Site Safety Induction
Training Topic 2 : | Advance First Aid
Training Topic 3 : | N/A
Number of Safety TBT | 2
TBT Topic 1 : | Respiratory Protection Practices (RPE)
TBT Topic 2 : | Risk Assessment & Work Methods Training
TBT Topic 3 : | N/A
TBT Topic 4 : | N/A
TBT Topic 5 : | N/A
Safety Awards and Recognitions | N/A
Recommendations and Improvements | N/A

## MAR
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba School
Reporting Period | MAR
Total Working Days a month | 21
Total Number of Workers | 37
Total Man-Hours Worked | 6216
Safety Performance :
Number of Safety Inspections | 2
Number of Safety Observation Raised | 4
Number of Safety Observation Closed | 4
External HSE Inspection / Audits | 2 | Tasneef & Fire Safety
Number of Safety Meetings Held | 1
Near Miss Reported | 1
Emergency Drills and Preparedness | 2
Incident Reporting :
Elevator | 0
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 0
Occupational Illness/Diseases | 0
Mdical Treatment Case | 0
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 0
Water Leaks/ Flooding | MEP LOG
Incident Frequency Rates
LTIFR - Lost Time Injury Frequency Rate | 0
TRIR - Total Recordable Incident Rate | 1
Training and Safety Programs
Number of Safety Trainings | 2
Training Topic 1 : | Fire Emergency Evacuation
Training Topic 2 : | Accident, Incident and Near Miss Reporting and it's Importance
Training Topic 3 : | N/A
Number of Safety TBT | 5
TBT Topic 1 : | Accident, Incident and Near Miss Reporting and it's Importance
TBT Topic 2 : | Storage of Fuels, chemicals and Oils and their Spill Control
TBT Topic 3 : | Emergency Eye Wash Stations Safety Training
TBT Topic 4 : | Store Management : Storage of Fuels, chemicals and Oils and hazardous substances
TBT Topic 5 : | Fire Emergency Response Actions
Safety Awards and Recognitions | N/A
Recommendations and Improvements | N/A

## APR
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba School
Reporting Period | APR
Total Working Days a month | 12
Total Number of Workers | 37
Total Man-Hours Worked | 3552
Safety Performance :
Number of Safety Inspections | 1
Number of Safety Observation Raised | 6
Number of Safety Observation Closed | 6
External HSE Inspection / Audits | 0
Number of Safety Meetings Held | 1
Near Miss Reported | 0
Emergency Drills and Preparedness | 1
Incident Reporting :
Elevator | 0
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 0
Occupational Illness/Diseases | 0
Mdical Treatment Case | 0
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 0
Water Leaks/ Flooding | MEP LOG
Incident Frequency Rates
LTIFR - Lost Time Injury Frequency Rate | 0
TRIR - Total Recordable Incident Rate | 0
Training and Safety Programs
Number of Safety Trainings | 1
Training Topic 1 : | Civil Defense Evacuation Drill
Training Topic 2 : | N/A
Training Topic 3 : | N/A
Number of Safety TBT | 0
TBT Topic 1 : | N/A
TBT Topic 2 : | N/A
TBT Topic 3 : | N/A
TBT Topic 4 : | N/A
TBT Topic 5 : | N/A
Safety Awards and Recognitions | N/A
Recommendations and Improvements | N/A

## MAY
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba School
Reporting Period | MAY
Total Working Days a month | 23
Total Number of Workers | 37
Total Man-Hours Worked | 6808
Safety Performance :
Number of Safety Inspections | 2
Number of Safety Observation Raised | 8
Number of Safety Observation Closed | 8
External HSE Inspection / Audits | 0
Number of Safety Meetings Held | 1
Near Miss Reported | 0
Emergency Drills and Preparedness | 0
Incident Reporting :
Elevator | 0
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 3
Occupational Illness/Diseases | 0
Mdical Treatment Case | 1
Pendamic Illness | 0
Physical Assault | 1 | Khidmah staff/ Contractor
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 0
Water Leaks/ Flooding | MEP LOG
Incident Frequency Rates
LTIFR - Lost Time Injury Frequency Rate | 0
TRIR - Total Recordable Incident Rate | 6
Training and Safety Programs
Number of Safety Trainings | 4
Training Topic 1 : | Risk Assessment, Method of Work & Standard Operating Procedures
Training Topic 2 : | Violence in workplace & Control of Substances Hazardous to Health - & HSE induction for the parents
Training Topic 3 : | Working in Heat/Summer Safety
Number of Safety TBT | 1
TBT Topic 1 : | Working in Heat/Summer Safety | To contractors
TBT Topic 2 : | N/A
TBT Topic 3 : | N/A
TBT Topic 4 : | N/A
TBT Topic 5 : | N/A
Safety Awards and Recognitions | N/A
Recommendations and Improvements | N/A

## JUNE
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Al Nokhba School
Reporting Period | June
Total Working Days a month | 15
Total Number of Workers | 37
Total Man-Hours Worked | 4440
Safety Performance :
Number of Safety Inspections | 1
Number of Safety Observation Raised | 15
Number of Safety Observation Closed | 12 | Uneven flooring around the school, canteen, school outdoor premises & at theatre stage - Qumra - adeed to the snagging list
External HSE Inspection / Audits | 0
Number of Safety Meetings Held | 1
Near Miss Reported | 3
Emergency Drills and Preparedness | 0
Incident Reporting :
Elevator | 0
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 1
Occupational Illness/Diseases | 0
Mdical Treatment Case | 0
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 1 | NAFFCO
Water Leaks/ Flooding | MEP LOG
Incident Frequency Rates
LTIFR ( Lost Time Injury Frequency Rate ) | 0
TRIR ( Total Recordable Incident ) | 2
Training and Safety Programs
Number of Safety Trainings | 1
Training Topic 1 : | Incident and accident reporting system
Training Topic 2 :
Training Topic 3 :
Number of Safety TBT | 0
TBT Topic 1 :
TBT Topic 2 :
TBT Topic 3 :
TBT Topic 4 :
TBT Topic 5 :
Safety Awards and Recognitions
Recommendations and Improvements

## JULY
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba School
Reporting Period | July
Total Working Days a month | 13
Total Number of Workers | 37
Total Man-Hours Worked | 3848
Safety Performance :
Number of Safety Inspections | 1
Number of Safety Observation Raised | 15
Number of Safety Observation Closed | 14 | Uneven flooring around the school, canteen, school outdoor premises & at theatre stage - Qumra - adeed to the snagging list
External HSE Inspection / Audits | 0
Number of Safety Meetings Held | 0
Near Miss Reported | 3
Emergency Drills and Preparedness | 0
Incident Reporting :
Elevator | 0
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 0
Occupational Illness/Diseases | 0
Mdical Treatment Case | 0
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 0
Water Leaks/ Flooding | MEP LOG
Incident Frequency Rates
LTIFR ( Lost Time Injury Frequency Rate ) | 0
TRIR ( Total Recordable Incident ) | 3
Training and Safety Programs
Number of Safety Trainings | 2
Training Topic 1 : | Electrical Safety & Chemical Spillage | Contractor
Training Topic 2 : | PAT Test & Emergency Prepardness plan | Contractor
Training Topic 3 :
Number of Safety TBT | 3
TBT Topic 1 : | Theft Prevention Safety | Contractor
TBT Topic 2 : | Dust Safety | Contractor
TBT Topic 3 : | Bus Safety | Contractor
TBT Topic 4 :
TBT Topic 5 :
Safety Awards and Recognitions
Recommendations and Improvements

## AUG
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba
Reporting Period | Aug
Total Working Days a month | 15
Total Number of Workers | 45
Total Man-Hours Worked | 5400
Safety Performance :
Number of Safety Inspections | 2
Number of Safety Observation Raised | 25
Number of Safety Observation Closed | 22
External HSE Inspection / Audits | 0
Number of Safety Committee/ Principal Meetings Held | 4
Near Miss Reported | 3
Emergency Drills and Preparedness | 2
Incident Reporting :
Elevator | 0
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 0
Occupational Illness/Diseases | 0
Mdical Treatment Case | 0
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 0
Water Leaks/ Flooding | MEP Log
Incident Frequency Rates
LTIFR ( Lost Time Injury Frequency Rate ) | 0
TRIR ( Total Recordable Incident ) | 3
Training and Safety Programs
Number of Safety Trainings | 6
Training Topic 1 : | HSE Induction | All school staff, HK, Security, qumra, emirates transport, Maintenance
Training Topic 2 : | Fire Evacuation Awarness | All school staff, HK, Security, qumra, emirates transport, Maintenance
Training Topic 3 : | FIrt Aid - CPR - By Batool | All School staff, HK, Security, qumra, emirates transport, Maintenance
Number of Safety ToolBoxTraining | 5
TBT Topic 1 : | Slip,Trip | Given by khidmah to there staff
TBT Topic 2 : | Lone Working
TBT Topic 3 : | 3R's - Reduce, Re Use & Re Cycle
TBT Topic 4 : | Manual Handling
TBT Topic 5 : | Working In Heavy Winds
Safety Awards and Recognitions
Recommendations and Improvements

## SEP
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba school
Reporting Period | Sep
Total Working Days a month | 21
Total Number of Workers | 47
Total Man-Hours Worked | 7896
Safety Performance :
Number of Safety Inspections | 1
Number of Safety Observation Raised | 20
Number of Safety Observation Closed | 17 | FF arch hole - Backside KG gate - Piller padding
External HSE Inspection / Audits | 1 | Khidmah quality dept. on there staff
Number of Safety Meetings Held | 4
Near Miss Reported | 3
Emergency Drills and Preparedness | 1
Incident Reporting :
Elevator | 0
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 2
Occupational Illness/Diseases | 0
Medical Treatment Case | 1
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 0
Water Leaks/ Flooding | MEP Log
Incident Frequency Rates
LTIFR ( Lost Time Injury Frequency Rate ) | 0
TRIR ( Total Recordable Incident ) | 6
Training and Safety Programs
Number of Safety Trainings | 3
Training Topic 1 : | Fire evacuation Drill | All students , staff , visitors , contractors
Training Topic 2 :
Training Topic 3 : | Safeguardian | SPARK
Number of Safety TBT | 5
TBT Topic 1 : | Working In Heavy Winds | Khidmah
TBT Topic 2 : | I See I Fix | Khidmah
TBT Topic 3 : | Personal Hygiene | Khidmah
TBT Topic 4 : | Uniform Guidelines | Khidmah
TBT Topic 5 :
Safety Awards and Recognitions
Recommendations and Improvements

## OCT
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba school
Reporting Period | OCT
Total Working Days a month | 17
Total Number of Workers | 46
Total Man-Hours Worked | 6256
Safety Performance :
Number of Safety Inspections | 1
Number of Safety Observation Raised | 20
Number of Safety Observation Closed | 18
External HSE Inspection / Audits | 0
Number of Safety Meetings Held | 4
Near Miss Reported | 5
Emergency Drills and Preparedness | 0
Incident Reporting :
Elevator | 0
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 1
Occupational Illness/Diseases | 0
Mdical Treatment Case | 1
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 0
Water Leaks/ Flooding | MEP Log
Incident Frequency Rates
LTIFR ( Lost Time Injury Frequency Rate ) | 0
TRIR ( Total Recordable Incident ) | 2
Training and Safety Programs
Number of Safety Trainings | 1
Training Topic 1 : | Refresh Induction, SOP Briefing | Facilities Department Team
Training Topic 2 :
Training Topic 3 :
Number of Safety TBT | 3
TBT Topic 1 : | Fire Safety, Emergency Response Actions and First Aid | Facilities Department Team
TBT Topic 2 : | Safe use of staircase | Maintenance team
TBT Topic 3 : | Electrical Safety | Maintenance team
TBT Topic 4 :
TBT Topic 5 :
Safety Awards and Recognitions
Recommendations and Improvements

## NOV
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba school
Reporting Period | NOV
Total Working Days a month | 21
Total Number of Workers | 48
Total Man-Hours Worked | 8064
Safety Performance :
Number of Safety Inspections | 2
Number of Safety Observation Raised | 25
Number of Safety Observation Closed | 25
External HSE Inspection / Audits | 0
Number of Safety Meetings Held | 4
Near Miss Reported | 4 | TBD
Emergency Drills and Preparedness | 1 | All school
Incident Reporting :
Elevator | 1 | Not operational - reception
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 0
Occupational Illness/Diseases | 0
Mdical Treatment Case | 0
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 1
Theft | 0
Third Party Non Compliance with Procedures | 2 | Qumra - Security incident report recorded // KHIDMAH misuse of chemical usage
Unauthorized Third Party Activity | 1 | KHIDMAH misuse of chemical usage
Water Leaks/ Flooding | MEP LOG
Incident Frequency Rates
LTIFR ( Lost Time Injury Frequency Rate ) | 0
TRIR ( Total Recordable Incident ) | 2
Training and Safety Programs
Number of Safety Trainings | 2
Training Topic 1 : | Emergency Evacuation Drill | All School occupents
Training Topic 2 : | Supervision procedure briefing | All Staff
Training Topic 3 :
Number of Safety TBT | 3
TBT Topic 1 : | Access control and visitors sign in | Security
TBT Topic 2 :
TBT Topic 3 :
TBT Topic 4 :
TBT Topic 5 :
Safety Awards and Recognitions
Recommendations and Improvements

## DEC
HEALTH, SAFETY, ENVIRONMENT (HSE) MONTHLY REPORT
Summary Information :
Project Name | Al Nokhba school
Reporting Period | DEC
Total Working Days a month | 8
Total Number of Workers | 46
Total Man-Hours Worked | 2944
Safety Performance :
Number of Safety Inspections | 1
Number of Safety Observation Raised | 11
Number of Safety Observation Closed | 0
External HSE Inspection / Audits | 0
Number of Safety Meetings Held | 2
Near Miss Reported | 0
Emergency Drills and Preparedness | 0
Incident Reporting :
Elevator | 1 | Not operational - receiption
Environmental Incidents | 0
Work related Fetality (FAT) | 0
Fire | 0
LTI - Reportable Injuries/ Permanenant Partial Disability | 0
Major Injuries/Permanent total Disability | 0
Minor Injury - First Aid Case | 0
Occupational Illness/Diseases | 0
Mdical Treatment Case | 0
Pendamic Illness | 0
Physical Assault | 0
Property Damage | 0
Theft | 0
Third Party Non Compliance with Procedures | 0
Unauthorized Third Party Activity | 0
Water Leaks/ Flooding | MEP LOG
Incident Frequency Rates
LTIFR ( Lost Time Injury Frequency Rate ) | 0
TRIR ( Total Recordable Incident ) | 0
Training and Safety Programs
Number of Safety Trainings | 1
Training Topic 1 : | HSE INDUCTION | Security - Khidmah staff
Training Topic 2 :
Training Topic 3 :
Number of Safety TBT | 4
TBT Topic 1 : | No Drugs & Smoking Policy | KHIDMAH
TBT Topic 2 : | Safety sign & their meanings | KHIDMAH
TBT Topic 3 : | Safe manual handling for shifting school furniture | KHIDMAH
TBT Topic 4 : | Barricades & warning signs | KHIDMAH | Security
TBT Topic 5 :
Safety Awards and Recognitions
Recommendations and Improvements

## DASHBOARD
Reporting Period | Number of Working Days | Number of Workers | Number of Man-Hours Worked | Number of Safety Inspections | Number of Safety Concerns Raised | Number of Safety Observation Closed | External HSE Inspection / Audits | Number of Safety Meetings Held | Near Miss Reported | Emergency Drills and Preparedness | Elevator | Environmental Incidents | Fatalities | Fire | LTI - Reportable Injuries/Temp Disability | Major Injuries/Permanent Disability | Minor Injury - First Aid Treatment | Occupational Illness/Diseases | Medical Treatment Case | Pendamic Illness | Physical Assault | Property Damage | Theft | Third Party Non Compliance with Procedures | Unauthorized Third Party Activity | Water Leaks/ Flooding | LTIFR | TRIR | Number of Safety Trainings | Number of Safety TBT
JAN | 21 | 37 | 6216 | 1 | 6 | 5 | 0 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEP LOG | 0 | 1 | 2 | 4
FEB | 21 | 37 | 6216 | 1 | 7 | 7 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEP LOG | 0 | 2 | 2 | 2
MAR | 21 | 37 | 6216 | 2 | 4 | 4 | 2 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEP LOG | 0 | 1 | 2 | 5
APR | 12 | 37 | 3552 | 1 | 6 | 6 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEP LOG | 0 | 0 | 1 | 0
MAY | 23 | 37 | 6808 | 2 | 8 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | MEP LOG | 0 | 6 | 4 | 1
June | 15 | 37 | 4440 | 1 | 15 | 12 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | MEP LOG | 0 | 2 | 1 | 0
July | 13 | 37 | 3848 | 1 | 15 | 14 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEP LOG | 0 | 3 | 2 | 3
Aug | 15 | 45 | 5400 | 2 | 25 | 22 | 0 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEP Log | 0 | 3 | 6 | 5
Sep | 21 | 47 | 7896 | 1 | 20 | 17 | 1 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | MEP Log | 0 | 6 | 3 | 5
OCT | 17 | 46 | 6256 | 1 | 20 | 18 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | MEP Log | 0 | 2 | 1 | 3
NOV | 21 | 48 | 8064 | 2 | 25 | 25 | 0 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | MEP LOG | 0 | 2 | 2 | 3
DEC | 8 | 46 | 2944 | 1 | 11 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEP LOG | 0 | 0 | 1 | 4
Total | 208 | 491 | 67856 | 16 | 162 | 138 | 4 | 24 | 27 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 3 | 0 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 28 | 27 | 35